## Slide 1
Presentation to Joint Portfolio Committee
29 July 2026

## Slide 2
Presentation Outline
Assessment of annual reports in terms of section 47 of MSA
Progress on the implementation of AGSA recommendations
Status of FRP

## Slide 3
Assessment of annual reports in terms of section 47 of MSA

## Slide 4
LEGISLATIVE COMPLIANCE
Section 47(1) of the Local Government: mandates that the Member of the Executive Council (MEC) for local government must annually compile and submit a consolidated report on municipal performance within the province to the provincial legislature and the Minister. In terms of Section 47(2), this report must fulfil the following statutory requirements:
Identify underperforming municipalities during the financial year.
Propose appropriate remedial actions.
Publish the findings in the Provincial Gazette.

## Slide 5
SUPPORT TO MUNICIPALITIES PERFORMANCE MONITORING
Activity | Progress | Purpose
Support municipalities on Institutionalisation of Performance Monitoring Systems which would culminate in the development on Section 46 Annual Performance Report. | Provincial LG: PMS Workshop 10 & 16 October 2025. Supported municipalities on quarterly performance reporting as per section 52 of the MSA through Circular 88 and institutionalisation of PMS. | CoGTA provided support on institutionalization of PMS to municipalities (Municipal Managers and Administration). Comparatively, in August 2024, municipalities were not reporting on Performance information which is a culmination of PMS. As at November 2025, 91% of municipalities submitted reports on Circular 88.
Workshop municipal officials (Municipal Manager and administration) on the draft municipal Annual Report and Oversight Reports. | Municipal Manager and administration officials workshopped on the draft municipal Annual Report and Oversight Reports 22 January 2026. | Workshop municipalities on status of the development of the Section 46 reports on the: Monitor progress of municipalities in developing Section 46 reports. Assess readiness of municipalities to table draft section 46 reports to council by 31 January 2026. Identify and share best practices. Letters of Non-compliance written to outstanding Municipalities.

## Slide 6
SUPPORT TO MUNICIPALITIES PERFORMANCE MONITORING
Activity | Progress | Purpose
Workshop MPAC chairpersons and officials on the draft municipal Annual Report and Oversight Reports consolidation in collaboration with AGSA. | MPAC chairpersons and officials workshopped on the draft municipal Annual Report and Oversight Reports 18 February 2026 | To provide an update and discuss the status of tabling the final 2024/2025 Annual Reports which must include the MPAC Oversight report compiled in terms of Section 129 of MFMA by 31 March 2026 Guide MPAC Chairpersons' in reviewing the draft municipal annual reports, thus strengthening municipal compliance and accountability in line with MFMA Section 129
Provincial meeting to assess municipalities state of readiness for tabling the final draft 2024/2025 MFMA section 129 reports | Provincial meeting convened 18 March 2026 to assess municipalities state of readiness for tabling the final draft 2024/2025 MFMA section 129 reports | Municipalities to provide an update on the status of tabling 2024/2025 Oversight reports on annual reports by 31 March 2026 Platform for municipalities to share lessons learned Identify best practices for future standardisation of the development of oversight reports on annual reports

## Slide 7
Annual Reports Submission rate to COGTA
Municipality | Tabling to Council | Submission
Mangaung Metro | 29 January 2026 | 29 January 2026
Xhariep DM | 29 January 2026 | 29 January 2026
Kopanong LM | Council Resolution outstanding | 09 February 2026
Letsemeng LM | 29 January 2026 | 01 February 2026
Mohokare LM | Not Submitted | Not Submitted
Lejweleputswa DM | 30 January 2026 | 04 February 2026
Masilonyana LM | 30 January 2026 | 04 February 2026
Matjhabeng LM | 29 January 2026 | 02 February 2026
Nala LM | Not Submitted | Not Submitted
Tokologo LM | 30 January 2026 | 04 February 2026
Tswelopele LM | 23 January 2026 | 23 January 2026

## Slide 8
Annual Reports Submission rate to COGTA
Municipality | Tabling to Council | Submission
Thabo Mofutsanyana DM | 30 January 2026 | 03 February 2026
Maluti-a-Phofung LM | 29 January 2026 | 04 February 2026
Mantsopa LM | 29 January 2026 | 04 February 2026
Nketoana LM | 29 January 2026 | 04 February 2026
Phumelela LM | 30 January 2026 | 06 February 2026
Setsoto LM | 30 January 2026 | 04 February 2026
Fezile Dabi DM | 27 January 2026 | 28 January 2026
Mafube LM | 30 January 2026 | 04 February 2026
Metsimaholo LM | 30 January 2026 | 02 February 2026
Moqhaka LM | 29 January 2026 | 30 January 2026
Ngwathe LM | 26 January 2026 | 06 February 2026

## Slide 9
Oversight Reports Submission rate to the FS Legislature
Municipality | Date
Xhariep DM | 08 April 2026
Lejweputswa DM | 16 April 2026
Masilonyana LM | 08 April 2026
Matjhabeng LM | 07 April 2026
Tokologo LM | 01 April 2026
Tswelopele LM | 02 April 2026
Thabo Mofutsanyana DM | 07 April 2026
Dihlabeng LM | 01 April 2026
Phumelela LM | 08 April 2026
Mantsopa LM | 13 April 2026
Setsoto LM | 07 April 2026

## Slide 10
Oversight Reports Submission rate to the FS Legislature
Municipality | Date
Fezile Dabi DM | 02 April 2026
Mafube LM | 02 April 2026
Metsimaholo LM | 02 April 2026
Moqhaka LM | 13 April 2026
*Oversight Report is a demonstration of the actual adopted Annual Report. | 

## Slide 11
Oversight Reports Submission rate to the FS Legislature – 08 Outstanding
Municipality | Date
Mangaung Metropolitan | Not submitted
Kopanong LM | Not submitted
Letsemeng LM | Not submitted
Mohokare LM | Not submitted
Nala LM | Not submitted
Maluti-a-Phofung LM | Not submitted
Nketoana LM | Not submitted
Ngwathe LM | Not submitted
Non-compliance letters sent to outstanding municipalities. | 

## Slide 12
Challenges & Remedial Action
In accordance with section 47(2)(b) of the Systems Act the MEC is required to propose remedial actions that will mitigate the challenges faced by municipalities.
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA 1: Public Participation (Putting People First) and Good Governance | 
Ward Constituency Meetings (Ward Meetings) | 
Compliance Deficits in Public Engagement A major governance risk is the widespread failure of ward councillors to consistently convene mandatory ward committee and public feedback meetings. This operational breakdown breaches the statutory mandates set out in the Local Government: Municipal Structures Act, which requires elected officials to maintain regular reporting lines with residents. | Intergovernmental Oversight, Capacity Building, and Public Participation Frameworks Targeted Municipal Capacity Building and Support Interventions The Department of Cooperative Governance and Traditional Affairs (CoGTA) must institutionalise structured support interventions to stabilize struggling local government administrations: ▪ Strategic Training Workshops: Initiate targeted capacity building sessions and technical training workshops specifically engineered for designated underperforming municipalities.

## Slide 13
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA 1: Public Participation (Putting People First) and Good Governance | 
Ward Constituency Meetings (Ward Meetings) | 
Inadequate Accountability Documentation The challenge of not convening meetings is severely compounded by a critical lack of administrative evidence: ▪ Absence of Verifiable Proof: Supported municipalities consistently present insufficient, poor-quality, or entirely non-existent evidence – such as signed attendance registers, official minutes, or public notices to prove that community feedback sessions occurred. ▪ Audit and Oversight Exposure: This complete deficit of physical and digital verification means that public participation claims cannot be legally validated during internal audits or provincial oversight reviews. | ▪ Remedial Action Interventions: Convene dedicated operational forums with poor-performing municipalities to critically diagnose localized administrative bottlenecks and formalize binding remedial action roadmaps. ¨ Legislative Oversight and Speakers' Governance Frameworks To fortify accountability and strengthen the oversight role of council leadership, the reporting and institutional structures of Council Speakers must be modernized:

## Slide 14
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA 1: Public Participation (Putting People First) and Good Governance | 
Ward Constituency Meetings (Ward Meetings) | 
 | ▪ Statutory Council Submissions: Mandate the formal tabling of Speakers' quarterly oversight reports – complete with actionable governance recommendations directly to full municipal councils. ▪ Institutional Repositioning of Forums: Strategically enhance, re-establish, and reposition District and Provincial Speakers' Forums to serve as high-impact platforms for legal compliance and peer accountability.

## Slide 15
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA 1: Public Participation (Putting People First) and Good Governance | 
Ward Constituency Meetings (Ward Meetings) | 
 | ▪ Intergovernmental Reporting Integration: Enforce the statutory presentation of Speakers' quarterly compliance reports across the following strategic intergovernmental alignment structures: District and Provincial Speakers' Forums Provincial Legislature Cluster Committee Sessions Broad Intergovernmental Relations (IGR) Forums  Public Participation Coordination and Secretariat Alignment To optimize local democratic structures and bridge communication gaps between municipalities and communities, administrative oversight networks must be streamlined: ▪ Secretariat Synchronization: Convene regular, structured alignment meetings linking municipal public participation practitioners, public relations officers, and dedicated district ward committee secretariats. This coordination ensures uniform operational standards and rigorous performance tracking across all municipal wards.

## Slide 16
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA 1: Public Participation (Putting People First) and Good Governance | 
Ward Committee | 
Ward Committee Dysfunction and Reporting Deficits Structural and Operational Dysfunction Ward committees across multiple municipalities are severely dysfunctional, failing to serve as effective statutory platforms for grassroots community participation. This institutional collapse is driven by a systemic failure to adhere to basic meeting protocols and legislative mandates: ▪ Pervasive Lack of Quorum: Meetings routinely fail to sit due to the consistent absence of committee members, which prevents the legal adoption of resolutions and stalls local decision-making. | Enhancing Ward Committee Governance and Documentation Compliance To resolve systemic ward committee dysfunction, eradicate the lack of quorums, and secure verifiable administrative records, CoGTA and the Office of the Speaker must urgently enforce the following strategic actions: Governance Enforcement and Functional Oversight Enforce Consequence Management: Establish strict administrative mechanisms within the Rules of Council to penalize ward councillors who fail to regularly convene statutory ward meetings. Link Stipends to Verified Performance: Mandate that out-of-pocket stipends for ward committee members be strictly conditional upon confirmed meeting attendance and the submission of qualitative sectoral reports.

## Slide 17
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA 1: Public Participation (Putting People First) and Good Governance | 
Ward Committee | 
Non-existent Portfolio Alignment: Committee members do not actively represent or engage their assigned community sectors, rendering the committee structure uncoordinated and inert.  Inadequate Administrative Evidence and Verification The operational failure of these committees is compounded by a critical lack of verifiable administrative documentation: ▪ Absence of Meeting Evidence: Municipalities consistently fail to produce authentic, compliant proof—such as signed attendance registers, formal meeting minutes, or official public notices—to confirm that ward committee sessions ever took place. | ▪ Implement Mandatory Alternate Systems: Amend local ward committee operational guidelines to include the formal appointment of alternate members to mitigate chronic quorum failures. ¨ Standardisation of Administrative Evidence ▪ Standardize Evidence Protocols: Issue a binding provincial directive outlining the non-negotiable compliance bundle required for every meeting: a signed attendance register, formal minutes, a clear agenda, and a written chairperson's report.

## Slide 18
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA 1: Public Participation (Putting People First) and Good Governance | 
Ward Committee | 
▪ Deficit of Sectoral Reports: There is an acute shortage or complete absence of written work and sectoral reports, making it impossible to evaluate if committee members are performing their designated duties. ▪ Audit and Compliance Vulnerability: This complete deficit of documentation leaves public participation claims unverified, exposing local municipalities to negative findings during provincial oversight reviews and Auditor-General (AG) governance audits. | officers must upload geo-tagged, time-stamped photos of meetings alongside digitized copies of attendance registers within 48 hours of any session. ▪ Institutionalize Quarterly Evidence Audits: Instruct District Ward Committee Secretariats to conduct rigorous, independent quarterly audits of all public participation records to ensure total alignment ahead of Auditor-General (AG) governance assessments. ¨ Capacity Building and Sectoral Accountability ▪ Roll Out Targeted Training Workshops: Launch immediate capacity-building programs focused on minute-taking, basic governance protocols, and effective meeting chairmanship for ward committee secretaries and public participation practitioners. ▪ Enforce Mandatory Sector Reporting: Require each ward committee member to submit a monthly, standardized one-page "Sector Work Report" detailing active engagements within their designated portfolios (e.g., youth, business, women, or disabled sectors).

## Slide 19
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA: Basic Service Delivery | 
Free Basic Services | 
Municipalities face several operational, structural, and institutional challenges that hinder the effective, equitable, and sustainable delivery of Free Basic Services (FBS). Indigent Register Management and Data Integrity Low and delayed registration: Many eligible indigent households do not register due to various socio-economic reasons, while municipal registration processes remain slow. Poor database maintenance: Regular, annual cleaning of indigent registers is often neglected, leading to data degradation. Inclusion errors: Unqualified individuals are sometimes entered into the database, compromising register integrity. Delayed service delivery: Administrative bottlenecks delay the rollout of services to households even after successful registration. Exclusion of Vulnerable Groups and Informal Dwellers Account-holder bias: Municipalities often restrict registration to households with formal municipal accounts, effectively excluding backyard dwellers and informal settlement residents. Department should develop a comprehensive policy framework specifically addressing the provision of Free Basic Services to backyard dwellers. | To address the identified challenges, the Directorate, in collaboration with the municipalities, will implement the following corrective measures: Enforce ongoing monitoring: Conduct continuous tracking and evaluation of municipal FBS and indigent subsidisation policy implementation. Roll out communication frameworks: Workshop and support municipalities on the newly developed FBS Communication Strategy to improve community awareness. Accelerate indigent registration: Streamline municipal administration to fast-track the enrolment of eligible indigent households. Mandate regular register updates: Conduct routine database reviews and cleanings to maintain indigent register integrity. Install water infrastructure: Roll out widespread water meter installations to accurately measure consumption and manage allocations. Improve beneficiary targeting: Refocus FBS delivery models to target the poorest households directly, ensuring fiscal sustainability. accommodate and support child-headed households. 7. Capacitate municipal teams: Appoint dedicated, specialized personnel to manage and oversee institutional FBS arrangements.

## Slide 20
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA: Municipal Financial Management and Viability (Sound Financial Management) | 
Audit Opinions | 
Non-attainment of clean audit Only one municipality – Dihlabeng LM improved to Unqualified opinion | Monitoring Audit Action plans
08 municipalities with Unfunded Budget | Collaborate with FS Provincial Treasure to support municipalities in consolidating credible budgets,
Decrease of R9,538,211,380 of UIFW expenditure for the province excluding the Mangaung Metro. | Support MPACs to deal with UIFW
Increase in uncollected debt | Support municipalities with operational effectiveness of local credit control and debt collection procedures.
Increased ESKOM Debt R26 243 754 873 Increased Water Boards Debt R8 761 197 019 | Monitor implementation of payment plans

## Slide 21
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA : Municipal Transformation and Organisational Development (Building Capable Municipalities) | 
Senior Management Vacancies and Service Delivery Impact Critical Executive Vacancies The province faces an unsustainably high vacancy rate within critical Section 54A (Municipal Managers) and Section 56 (Managers directly accountable to Municipal Managers) positions. This severe shortage of permanent, legally compliant executive leadership creates institutional instability and directly undermines municipal capability. Impact on Service Delivery The prolonged absence of permanent senior managers significantly weakens administrative oversight, stalls strategic infrastructure projects, and impairs basic service delivery to local communities. Without stable executive command, municipalities struggle to implement capital budgets, maintain regulatory compliance, and fulfil their constitutional mandates. | Regulatory Compliance Actions and MEC Directives To enforce administrative compliance and stabilize institutional governance across local government structures, the Department of Cooperative Governance and Traditional Affairs (CoGTA) has executed the following statutory measures: ▪ MEC Accountability Notifications: The Member of the Executive Council (MEC) has issued formal letters of non-compliance to all municipalities that have failed to review their organizational staff establishments or fill vacant critical positions. ▪ Section 139 Interventions: CoGTA has issued strict directives in terms of Section 139(1)(a) of the Constitution to municipalities failing to fill senior management vacancies within the legally regulated timeframes. These directives impose a mandatory three-month deadline to finalize the recruitment of senior executives. Departmental Municipal Capacity Support In tandem with enforcement actions, CoGTA is actively providing targeted administrative assistance to capacitate underperforming local municipalities: ▪ Organisational Structure Re-alignment: The Department is providing hands-on technical support to municipalities undergoing organizational structure reviews to ensure their staff establishments align with municipal mandates. ▪ Accelerated Recruitment Frameworks: CoGTA is driving the implementation of accelerated recruitment plans across supported municipalities, utilizing a strict three-month turnaround strategy to urgently populate critical institutional vacancies.

## Slide 22
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA 6: Local Economic Development | 
LED Strategies | 
Municipalities encounter critical structural and administrative constraints that hinder the successful execution and coordination of Local Economic Development initiatives. Identified LED Challenges Severe capacity constraints: LED Units suffer from a lack of skilled human resources, inadequate budgets, and a limited conceptual understanding of LED frameworks. Outdated strategic planning: Implementation remains weak due to outdated and non-credible municipal LED strategies. diverse stakeholders limits the adoption of a differentiated, tailored approach to local economic growth. | To address the identified challenges, the Directorate will implement the following coordination and capacity-building measures: Facilitate stakeholder platforms: Convene regular meetings with municipalities and key stakeholders to create an information-sharing platform for institutional best practices. Leverage statutory assessments: Use quarterly IDP evaluation sessions to actively engage municipalities and enforce integrated planning recommendations. Establish a Provincial Task Team: Form a dedicated technical team to directly assist municipalities with the comprehensive review and updating of their LED strategies.

## Slide 23
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA 6: Local Economic Development | 
LED Strategies | 
Key Administrative Priorities and Interventions Execute IDP recommendations: Implement the specific inputs and corrective measures identified during Integrated Development Plan (IDP) assessments. Develop regulatory frameworks: Draft, pass, and enforce municipal bylaws that directly support and regulate local economic activity. | Mobilise private sector forums: Identify and coordinate key commercial stakeholders to establish functional local Business Forums. Host bi-annual provincial forums: Convene the bi-annual Provincial LED meetings to align regional development agendas and track progress. Strengthen intergovernmental alignment: Engage with DESTEA and SALGA to coordinate provincial initiatives and synchronize economic development programs.

## Slide 24
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA 6: Local Economic Development | 
Community Works Programme | 
The National Department of Cooperative Governance (DCOG) did not appoint an external implementing agent for the 2024/25 financial year. Instead, Free State CoGTA managed and executed the programme internally. During the implementation phase, the Department encountered several operational and administrative obstacles: Severe Budgetary Constraints: Substantial funding reductions severely impeded core program operations, specifically restricting the recruitment and replacement of participants. Asset Management Ambiguity: A distinct lack of policy clarity hindered the proper disposal of obsolete assets. Procurement Delays: The program suffered from a total non-procurement of essential equipment. Workforce Absenteeism: High rates of absenteeism negatively impacted daily productivity and project continuity. | To address these challenges and improve future programme outcomes, the following strategic actions are recommended: Strategic Partnerships: Develop innovative collaboration strategies by establishing public and private partnerships to optimize resources. Budget Optimization: Secure an increased budget allocation specifically for the Community Works Programme (CWP) to restore operational capacity. System Integration: Regularly update the Management Information System (MIS) to accurately track, analyse, and determine non-wage performance costs.

## Slide 25
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA: Cross-cutting Initiatives in Supporting Municipalities | 
Integrated Development Planning | 
The evaluation of municipal IDPs is hindered by operational bottlenecks, a lack of preparation, and poor interdepartmental participation. Specifically, the following challenges were experienced: Non-compliance with timelines: Municipalities frequently fail to adhere to statutory legislative timeframes for submission. Delayed or absent evidence: IDP Managers regularly submit their portfolios of evidence late, or fail to submit them at all. Inconsistent documentation: Some municipal delegations bring a different version of the IDP document to the physical assessment sessions than the one originally submitted for evaluation. | To resolve the operational and compliance challenges experienced during evaluations, the Directorate will implement the following measures: Enforce timeframe compliance: Formally advise municipalities to adhere strictly to statutory legislative timeframes for all submissions. Secure supporting evidence: Encourage municipal delegations to bring all relevant portfolio of evidence documentation Standardise the baseline document: Restrict assessments exclusively to the official IDP documentation that was formally submitted to the CoGTA MEC.

## Slide 26
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA: Cross-cutting Initiatives in Supporting Municipalities | 
Integrated Development Planning | 
Inadequate preparation: Several municipalities do not familiarise themselves with the specific IDP assessment criteria and questions per Key Performance Area (KPA). | Report assessment discrepancies: Encourage municipalities to immediately notify CoGTA if sector commissions utilize questions that deviate from the standardized assessment template. Mobilise sector departments: Advise and encourage all provincial sector departments to ensure active, meaningful participation in the monitoring and evaluation of municipal IDPs.

## Slide 27
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA: Cross-cutting Initiatives in Supporting Municipalities | 
Spatial Planning and Land Use Management | 
Severe municipal capacity constraints A systemic deficiency in internal capacity severely hinders municipalities from fulfilling their statutory mandates. This is particularly evident with the Spatial Planning and Land Use Management Act (SPLUMA), which strictly obligates all local municipalities to draft and implement comprehensive, wall-to-wall Land Use Schemes (LUS). | Legislative Reform and Spatial Planning The Department of Cooperative Governance and Traditional Affairs (CoGTA) is currently drafting the Free State Spatial Planning and Land Use Management Bill. Once enacted, this legislation will significantly impact and necessitate revisions to existing Municipal Planning Bylaws across the province. Land Use Scheme Development and Operational Challenges

## Slide 28
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA: Cross-cutting Initiatives in Supporting Municipalities | 
Spatial Planning and Land Use Management | 
Severe municipal capacity constraints A systemic deficiency in internal capacity severely hinders municipalities from fulfilling their statutory mandates. This is particularly evident with the Spatial Planning and Land Use Management Act (SPLUMA), which strictly obligates all local municipalities to draft and implement comprehensive, wall-to-wall Land Use Schemes (LUS). | CoGTA is actively drafting Land Use Schemes (LUS) on behalf of local municipalities. However, the Directorate faces critical operational bottlenecks in completing 11 municipal schemes due to the following constraints: ▪ Capacity Limitations: Insufficient internal personnel within the Directorate to execute complex planning projects. ▪ Prohibitive Data Costs: High financial costs required to acquire essential property ownership and boundary information from the Registrar of Deeds. ▪ Funding Shortfalls: A severe lack of financial resources to appoint external professional consultants for specialized drafting support. [1] ¨ Technical and Administrative Municipal Capacity Support

## Slide 29
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA: Cross-cutting Initiatives in Supporting Municipalities | 
Disaster Management | 
The Free State Provincial Disaster Management Centre (PDMC) and its subsidiary municipal structures face acute operational, structural, and financial deficits that actively undermine regional disaster readiness and emergency coordination: ▪ Head Office Closure and Infrastructure Deficiencies: The Department of Employment and Labour formally flagged and closed the primary FS PDMC head offices due to hazardous, sub-standard working conditions. This closure severely cripples centralized coordination, command capabilities, and provincial response speeds. Furthermore, existing District Disaster Management Centre buildings routinely fail to satisfy minimum mandated regulatory infrastructure requirements. | To correct these institutional vulnerabilities and protect local communities from escalating environmental hazards, the Head of Department (HOD) and executive leadership must urgently drive the following actions: ▪ Urgent Workplace Remediation: Prioritize immediate budget allocation and intergovernmental collaboration to refurbish the provincial head offices, ensuring full compliance with health and safety laws to safely centralize disaster command operations. ▪ Infrastructure and Asset Upgrades: Formulate a strategic, multi-sphere funding model to upgrade district centre buildings until they successfully meet minimum infrastructure requirements. This includes elevating field resources—such as procuring specialized 4×4 emergency response vehicles and evaluating chopper/aerial partnerships—to standardise provincial rescue capacities.

## Slide 30
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA: Cross-cutting Initiatives in Supporting Municipalities | 
Disaster Management | 
Severe Budgetary Deprivation: There is currently a total absence of dedicated financial allocations for disaster risk reduction and emergency response budgets. This extreme fiscal constraint completely restricts the PDMC from deploying critical public awareness programs or executing identified risk-mitigation projects. | Mandatory Governance and Forum Activation: Issue strict administrative directives forcing all municipalities to regularly convene their local Disaster Management Advisory Forums. This is vital to synthesize joint decision-making, establish cross-sector response protocols, and close critical response gaps.

## Slide 31
Challenges & Remedial Action
Regulatory, Systemic and Operational Challenges | Municipal Support and Strategic Interventions
KPA: Cross-cutting Initiatives in Supporting Municipalities | 
Fire Services | 
The administration, governance, and deployment of firefighting services across the Free State Province are severely compromised by systemic legal non-compliance, leadership gaps, and structural resource deficits: ▪ Widespread Legislative Non-Compliance: Out of the entire province, only 12 local municipalities have established fire services that comply with basic legislative frameworks. It is a matter of grave concern that even among these 12 established services, operations are severely dysfunctional and fall far below mandated legislative standards. ▪ Complete Territorial Service Deficits: The Xhariep DM exhibits a total absence of fire safety infrastructure. It has failed to establish a functional fire services brigade in any of its constituent local municipalities, leaving local communities profoundly vulnerable to fire hazards. ▪ Critical Executive Leadership Vacancies: Multiple high-priority municipal jurisdictions, specifically the Mangaung Metro, Moqhaka LM, Ngwathe LM, and Dihlabeng LM, have failed to formally appoint Chief Fire Officers. This critical vacancy rate severely compromises administrative oversight and command accountability. | To resolve these critical governance and operational shortfalls, the Head of Department (HOD) and senior executive leadership must urgently implement the following strategic interventions: Enforce Chief Fire Officer Appointments: Issue immediate administrative directives to the councils of Mangaung Metro, Moqhaka LM, Ngwathe LM, and Dihlabeng LM to fast-track the recruitment and formal appointment of qualified Chief Fire Officers. Unblock Intergovernmental Fleet Assets: Engage in immediate, high-level bilateral discussions with the DFFE and the Free State Provincial Disaster Management Centre (FSPDMC) to resolve the MOU disputes. This is critical to secure the immediate release of the "Yellow Fleet" emergency vehicles to the provinces. Formalize and Align Regulatory Frameworks: Convene the planned two-day provincial fire management session to finalize and adopt a comprehensive provincial fire management plan. Ensure that the Provincial Fire Services Advisory Committee (ProFSAC) Terms of Reference are thoroughly reviewed and strictly aligned with the National Fire Services Advisory Committee (NAFSAC).

## Slide 32
Challenges & Remedial Action
  Challenges:
Capacity of the MPAC to deliberate on the Annual Report.
MPACs being bias on the Financial Performance information without considering Non-Financial information.
Remedial Action:
Administrative Capacitation of the MPAC by municipalities.
CoGTA will support the newly elected MPAC Chairpersons in order to ensure Oversight in municipalities.
MEC CoGTA has issued a Notice in terms of section 105 of MSA on section 52 of MSA to support municipalities towards ensuring quarterly municipal performance reports are developed and considered by Council for submission to CoGTA.
Ongoing PMS support on Policy Framework/Circular 88 MFMA and alignment.
Publication of draft Planning and Performance Regulations in collaboration with DCOG.

## Slide 33
Progress made in implementing AGSA recommendations

## Slide 34: AUDIT ACTION PLANS
The status of Audit Action Plans as per National Treasury Web Portal and the comparative analysis with the Management Reports are illustrated on the table below:
Differences between the Management Report and Audit Action Plan
Letsemeng: The Municipality did not upload all findings on the National Treasury Web Portal due to capacity constraints.
Kopanong: The Municipality did not upload all findings on the National Treasury Web Portal due to capacity constraints.
Mohokare: The Municipality did not upload all findings on the National Treasury Web Portal due to capacity constraints.

## Slide 35: AUDIT ACTION PLANS (CONT.)
The following table reflect the progress regarding the implementation of audit findings as reported on the National Treasury Web Portal:
District Audit Action Plan Forums were conducted as follows:
21 May 2026: Xhariep District Municipality and Mohokare Local Municipality

## Slide 36: UIF & W EXPENDITURE
Comparative analysis 2023/2024 – 2024/2025
The table below reflects an overall decrease of R140,064,668 of UIFW expenditure for the Xhariep District

## Slide 37: UIF & W EXPENDITURE (CONT.)
MPAC Investigations:
Xhariep DM: MPAC performed investigations, but recommendations was not tabled in Council.
Letsemeng and Kopanong LM: No investigations performed.
Mohokare LM: MPAC performed investigations, but recommendations was not tabled in Council.

## Slide 38: SUPPORT AND INTERVENTION MEASURES
Coordinated support from Provincial Treasury, COGTA and SALGA via the Municipal Revenue and Debt collection Forum.
Proposed monitoring, supporting, and reporting items for 2026/27
Revenue Collection Analysis
Valuation Roll Implementation
Credit Control Measures
Indigent Management
Meter Reading & Verification
Non-Revenue Water/Electricity Losses
Customer Services reporting
Policy Review
Tariff Review
Debt Relief Programmes
Annual Revenue Assessment Tool

## Slide 39: STATUS OF FRP
Four municipalities are under FRP:
  Mafube LM
  Tokologo LM
  Matjhabeng LM
  Mangaung MM

## Slide 40: Status of FRP - Mafube
Remain in rescue phase with slow improvement
Main reasons for remaining on rescue phase:
Financial viability
  Still not financially viable
  Unfunded budget
  Low revenue collection – average 22%
  Not able to pay salaries in time
  Creditors too high at R1.5 billion (Water and Sanitation – R652m; ESKOM – R429m, employee benefits – R264m)
  Qualified audit report

## Slide 41: Status of FRP - Mafube
Main reasons for remaining on rescue phase:
Governance
  Unstable and volatile labour relations due to the following:
  - Employees participated in an unprotected strike resulting in 7 Shop stewards
  being suspended pending disciplinary processes.
    Monies deducted from salaries of some employees (No-Work-No-Pay)
    Dismissal of the HR officer due to fraud case.
  No improvement on the following areas risk management, contract management, promulgation of by-laws due to capacity and financial difficulties.
Institutional Capacity
  Vacant senior managers position – MM, CFO, Director Technical Services
  Review and of the organizational structure & HR policies still outstanding
  Unstable labour relations caused by, among others, the current disciplinary processes instituted against shop stewards

## Slide 42: Status of FRP - Mafube
Main reasons for remaining on rescue phase:
Service delivery
Roads
The road network span 289 KM which is mostly in poor conditions
Lack of adequate yellow fleet and equipment to maintain roads
Water & Sanitation
Wastewater Treatment Works in Cornelia & Tweeling does not comply with set standards, thus needs upgrading
There is a current increase in the bucket system, especially in Tweeling, Cornelia & Villiers. For Namahadi, a project in Ext 9 for installation of Toilets is planned to commence later in the year.

## Slide 43: Status of FRP - Tokologo
The municipality is doing well with regard to the governance as all its governance committees are functional.
The municipality is doing well with also with regard to Institutional Capacity as all its senior management positions as well as critical vacancies are filled and policies have been reviewed and approved.
However, the municipality remain in rescue phase with this noticeable improvement.
Main reasons for remaining on rescue phase:
Financial viability
  Not financially viable
  Unfunded budget
  Low revenue collection
  SALA which is owed above R24 million
  The municipality does not service its debt with the department of Water and Sanition, as there is an issue that needs to be dealt with regarding the accounts.
  Qualified audit report

## Slide 44: Status of FRP - Tokologo
Main reasons for remaining on rescue phase:
Service delivery
Water
Inconsistent water supply in Hertzogville and Dealesville due to ageing infrastructure, vandalism and theft.
Boshof is 100% dependent on boreholes, however the supply is somehow stable.
Refuse removal
Refuse is not collected at 100% in all towns due to lack of refuse collection tractors.
The current refuse collection tractors are not in good condition, thus collection schedule is not adhered to.
Sewer
The municipality has a backlog of 313 buckets system and VIPs in Hertzogville and Dealesville.
There are minor sewer spillages that do occur and they are addressed on time when reported by the municipality.

## Slide 45: Status of FRP - Tokologo
Main reasons for remaining on rescue phase:
Service delivery
Roads & storm-water
General road maintenance is a challenge due to unavailability of funds.
Fleet
The municipality has old dilapidated yellow fleet which makes provision of basic services a challenge
Electricity
The municipality is still unable to pay the Eskom current account.
The report of the Minister has not yet been released on mediation process. However, the municipality is going to embark on the DAA process of partnership with Eskom.
The council had already approved the partnership in 2025.

## Slide 46: Status of FRP - Matjhabeng
Remain in rescue phase no improvement
Main reasons for remaining on rescue phase:
The municipality does not cooperate with the EXCO rep.
Does not attend the war room meeting which is a monitoring meeting.
Unfunded and Non-Compliant Budget
Contravention of Employment Moratorium
SIU investigation
Illegal EPWP Unit still not terminated
Non-adherence to reporting framework
Unlawful appointment of Acting Municipal Managers

## Slide 47: Status of FRP - Mangaung
Although Mangaung is under FRP, it is under the Cabinet Representative.
Therefore implementation of FRP is monitored by National Treasury.
However, the municipality remain in rescue phase.

## Slide 48
THANK YOU.
KE A LEBOHA
BAIE DANKIE
NDIYABULELA